## Sheet1
TASK
Sr no. | Screens | status | priority | UI | Integration | Backend | start date | end date
1 | user dashboard | done | high | Namita-done | Done | Amruta-done | 2021-11-16
2 | admin dashboard | done | high | Namita-done | Done | Akhil-done | 2021-11-17 | 2021-11-18
3 | manager dashboard | working | high | Namita-done | pending | Sarang-done | 2021-11-18
4 | Enroll Sports | Done | high | Ameya | done | Akhil
5 | subcategories | pending | medium
8 | payment | pending | medium | Ameya-done | done | Akhil | 2021-11-18
9 | Gallery | pending | low
10 | AboutUs | pending | low
11 | ContactUs | pending | low
12 | login | done | high | Sarang | Done | Hrishikesh | 2021-11-18
13 | UserRegistration | working | high | Sarang |  | Hrishikesh | 2021-11-18
14 | homepage | done | medium | Ameya |  |  | 2021-11-16 | 2021-11-16
15 | ManagerRegistration | pending | medium | Sarang |  | Hrishikesh
16 | AddSports | pending | medium | Akhil |  | Akhil
17 | Navbar | done | high | Namita-done | done | Namita-done | 2021-11-17 | 2021-11-17
18 | Database | done | high | Akhil | done | Akhil | 2021-11-15 | 2021-11-15
19 | activity | pending | low
20 | profile | done | medium | Akhil | Done | Akhil | 2021-11-17 | 2021-11-17
21 | changePassword | done | medium | Amruta-done | done | Amruta-done | 2021-11-16 | 2021-11-18
22 | ForgetPassword | pending | medium | Ameya-done | pending |  | 2021-11-18
23 | FeedBackSystem | pending | medium
24 | OTP | pending | medium | Ameya-done | pending |  | 2021-11-18
25 | like | pending | high |  | pending | Hrishikesh
26 | comment | pending | high |  | pending | Hrishikesh